## All Items
ID | Plan Set | Line Item | Missing Data | Source Needed | Status
MI-A-001 | GSW Cypress | 4" DIP fire line pipe | LF from tee to SS pipe | P-1 Detail 1 dimension | Unresolved
MI-A-002 | GSW Cypress | Sand/crushed rock/Class A/B concrete bedding | CY | Cypress Std. 324 trench width applied to 530.22 LF | Unresolved
MI-A-003 | GSW Cypress | AC pavement and slurry seal restoration | SY | P-1 trench/log limits in ROW | Unresolved
MI-B-001 | GSW Cypress | Title block vs plan count — IRR/FS | Confirm governing count | Engineer clarification (T-1 says 1 IRR/1 FS; plan shows 2 each) | Unresolved
MI-B-002 | Whittier Water | Thrust blocks, bedding, backfill, CMB, AC, curb/gutter | CY/SY/LF | Whittier Std. W-647 detail sheets | Unresolved
MI-C-001 | Tract 82457 Sewer | 8" VCP joint count | EA | Pipe laying length / joint type schedule | Unresolved
MI-C-002 | Tract 82457 Sewer | Precast manhole diameter and barrel depth | EA sizing | LACPW 2023-2 applied to rim/inv elevations | Unresolved
MI-C-003 | Tract 82457 Sewer | Manhole step count | EA | Manhole depth from profile | Unresolved
MI-C-004 | Tract 82457 Sewer | Terminal cleanout structures | EA | Plan symbol count | Unresolved
MI-C-005 | Tract 82457 Sewer | Neoprene bushings | EA | Cast-iron connection count | Unresolved
MI-C-006 | Tract 82457 Sewer | Concrete encasement | CY | Encasement station limits on profile | Unresolved
MI-C-007 | Tract 82457 Sewer | 12" proposed storm drain | LF | Page 2 plan measure | Unresolved
MI-C-008 | Tract 82457 Sewer | Bedding, backfill, AC resurfacing, pipe anchors | CY/SY/EA | SPPWC 2021-1 / 221-2 details + trench limits | Unresolved
MI-C-009 | Tract 82457 Sewer | 8" proposed water pipe material class | Spec | Water notes not included in sewer set | Unresolved

## SET A - GSW Cypress
ID | Plan Set | Line Item | Missing Data | Source Needed | Status
MI-A-001 | GSW Cypress | 4" DIP fire line pipe | LF from tee to SS pipe | P-1 Detail 1 dimension | Unresolved
MI-A-002 | GSW Cypress | Sand/crushed rock/Class A/B concrete bedding | CY | Cypress Std. 324 trench width applied to 530.22 LF | Unresolved
MI-A-003 | GSW Cypress | AC pavement and slurry seal restoration | SY | P-1 trench/log limits in ROW | Unresolved
MI-B-001 | GSW Cypress | Title block vs plan count — IRR/FS | Confirm governing count | Engineer clarification (T-1 says 1 IRR/1 FS; plan shows 2 each) | Unresolved

## SET B - Whittier Water
ID | Plan Set | Line Item | Missing Data | Source Needed | Status
MI-B-002 | Whittier Water | Thrust blocks, bedding, backfill, CMB, AC, curb/gutter | CY/SY/LF | Whittier Std. W-647 detail sheets | Unresolved

## SET C - Tract 82457 Sewer
ID | Plan Set | Line Item | Missing Data | Source Needed | Status
MI-C-001 | Tract 82457 Sewer | 8" VCP joint count | EA | Pipe laying length / joint type schedule | Unresolved
MI-C-002 | Tract 82457 Sewer | Precast manhole diameter and barrel depth | EA sizing | LACPW 2023-2 applied to rim/inv elevations | Unresolved
MI-C-003 | Tract 82457 Sewer | Manhole step count | EA | Manhole depth from profile | Unresolved
MI-C-004 | Tract 82457 Sewer | Terminal cleanout structures | EA | Plan symbol count | Unresolved
MI-C-005 | Tract 82457 Sewer | Neoprene bushings | EA | Cast-iron connection count | Unresolved
MI-C-006 | Tract 82457 Sewer | Concrete encasement | CY | Encasement station limits on profile | Unresolved
MI-C-007 | Tract 82457 Sewer | 12" proposed storm drain | LF | Page 2 plan measure | Unresolved
MI-C-008 | Tract 82457 Sewer | Bedding, backfill, AC resurfacing, pipe anchors | CY/SY/EA | SPPWC 2021-1 / 221-2 details + trench limits | Unresolved
MI-C-009 | Tract 82457 Sewer | 8" proposed water pipe material class | Spec | Water notes not included in sewer set | Unresolved